## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
Passenger
1 | Check in | As a passenger, I want to • Retrieve my own flight information So that I can make sure I get on the plane on time | very high | 1 | 1.Verify that passengers can retrieve their corresponding flight information 2.Verify that if the passenger's flight information is not retrieved, there is a pop-up alert | customer | 12 April | 23 April
2 | Choose food | As a passenger, I want to • Choose the type of food I eat on the plane So that I can make sure I won't starve on a plane | medium | 3 | Verify that one passenger can only choose one type of the food | customer | 25 April | 6 May
3 | Choose seat | As a passenger, I want to • Choose my own seat on the plane So that I can make I feel comfortable on the plane | high | 2 | 1.Verify that one passenger can only choose one seat 2. Verify the seat status can be seen by all passengers 3.Make sure if a seat is choosed by one passenger，other passengers can not choose it | customer | 29 March | 9 April
4 | Choose special service（food/seat） | As a passenger with special demand, I want to • Choose the exact meal I specify • Make the seat fit my special needs (extra legroom) So that I can make sure every detail is considered and the whole flight is more comfortable | high | 2 | Make sure that every passenger with special demand pay extra money for the service | customer | 12 April | 23 April
5 | Confirm check in | As a passenger, I want to • Review all my options for checking in So that I can make sure all the information is correct | high | 2 | 1.Verify that if passengers find that there is something wrong，they can go back to modify their information 2. Verify that all the information displays well | customer | 12 April | 23 April
6 | Print pass\tag\ticket | As a passenger, I want to • Print the information I need before boarding So that I can make sure I can board the plane without any worries | medium | 3 | 1.Verify that all the information displays well 2.Verify that things should be printed meet the needs of passengers at booking time | customer | 12 April | 23 April
Maintenance staff
19 | Check passenger list | As a Maintenance staff, I want to • know my duty information • know flight information • know the passenger list of the flight So that I can know the preparation time and the information about the flight and passengers | high | 2 | Passenger information shall be prominently displayed below the flight information | Maintenance staff | 25 April | 6 May
20 | Check check-in status | As a Maintenance staff, I want to • know the waiting status of passengers on my flight So that I can judge whether to remind passengers to board in time | high | 2 | Passenger boarding status shall be prominently displayed below the flight information | Maintenance staff | 26 April | 7 May
21 | Check passengers' seat options | As a Maintenance staff, I want to • know the details of passengers' seat choices on my flight So that I can judge whether to make additional preparations for passengers | medium | 3 | The passenger panel shall display the details of the passenger's seat requirements | Maintenance staff | 12 April | 23 April
18 | Check passengers' food options | As a Maintenance staff, I want to • know the details of the meal choices of the passengers on my flight So that I can judge whether to make additional preparations to serve the passengers | medium | 3 | The passenger panel shall display the details of the passenger's food needs | Maintenance staff | 10 May | 21 May
Administrator
26 | Change passenger list | As an administrator, I want to •Have the ability to change passenger list So that when I find somthing wrong in the passenger list I can correct it | high | 2 | 1.Verify user detail information can be displayed correctly 2.Verify that the administerer can change the passenger list and can save the new list. | admin | 29 March | 9 April
27 | Change check-in status | As an administrator, I want to •Have ability to change check-in status So that when passenger have checked in but want to alter something I can offer my help. | medium | 3 | 1. Verify user detail information can be displayed correctly. 2. Verify that the administerer can change the Check-in status and can save the new status. | admin | 26 April | 7 May
28 | Change passengers' seat options | As an administrator, I want to •Have ability to change passenger's seat options So that when passenger have confirmed but want to alter seat I can offer my help. | high | 2 | 1. Verify user detail information can be displayed correctly. 2. Verify that the administerer can change the seat options and can save the new status. | admin | 29 March | 9 April
29 | Change passengers' food options | As an administrator, I want to •Have ability to change passenger's food options So that when passenger have confirmed but want to alter food options I can offer my help. | high | 2 | 1. Verify coach detail information can be displayed correctly. 2. Verify that the administerer can change the food options and can save the new status. | admin | 12 April | 23 April